## Zaman Çizelgesi
Smart Home Automation System (by months)
|  |  |  | Şub-2021 | Şub-2021 | Şub-2021 | Şub-2021 | Mar-2021 | Mar-2021 | Mar-2021 | Mar-2021 | Mar-2021 | Nis-2021 | Nis-2021 | Nis-2021 | Nis-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | Haz-2021 | Haz-2021 | Haz-2021 | Haz-2021 | Tem-2021 | Tem-2021 | Tem-2021 | Tem-2021 | Ağu-2021 | Ağu-2021 | Ağu-2021 | Ağu-2021 | Ağu-2021 | Eyl-2021 | Eyl-2021 | Eyl-2021 | Eyl-2021 | Eki-2021 | Eki-2021 | Eki-2021
| Assigned to | Start | End | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18
Smart Home Automation System |  |  |  | 1: Smart Home Automation System
Project Proposal Report | Berk Önder | 06-Şub-2021 | 07-Şub-2021 | 1: Project Proposal Report (06-Şub-21 - 07-Şub-21)
Requirements Report | Berk Önder | 08-Şub-2021 | 28-Şub-2021 | 8: Requirements Report (08-Şub-21 - 28-Şub-21); 15: Requirements Report (08-Şub-21 - 28-Şub-21); 22: Requirements Report (08-Şub-21 - 28-Şub-21)
Architecture Report | Berk Önder | 01-Mar-2021 | 18-Mar-2021 | 1: Architecture Report (01-Mar-21 - 18-Mar-21); 8: Architecture Report (01-Mar-21 - 18-Mar-21); 15: Architecture Report (01-Mar-21 - 18-Mar-21)
Development and Test Report | Berk Önder | 19-Mar-2021 | 04-Nis-2021 | 15: Development and Test Report (19-Mar-21 - 04-Nis-21); 22: Development and Test Report (19-Mar-21 - 04-Nis-21); 29: Development and Test Report (19-Mar-21 - 04-Nis-21)
Final Report | Berk Önder | 05-Nis-2021 | 27-Nis-2021 | 5: Final Report (05-Nis-21 - 27-Nis-21); 12: Final Report (05-Nis-21 - 27-Nis-21); 19: Final Report (05-Nis-21 - 27-Nis-21); 26: Final Report (05-Nis-21 - 27-Nis-21)